# Pre-arrival Guest Journey - Proposal

Prepared for Harbor & Pine Hotels by Maya Lindqvist Consulting

Date: 21 May 2025

## Summary

Harbor & Pine Hotels runs three boutique hotels in Visby, Kalmar and Ystad with 128 rooms in total. Guests receive one generic confirmation email, and the front desk spends about two hours a day answering the same questions about parking, check-in times and breakfast. This proposal covers a pre-arrival guest journey: a personalised email seven days before arrival, a mobile check-in form and relevant offers.

## About Maya Lindqvist Consulting

Maya Lindqvist Consulting is a one-person product and service design practice based in Uppsala, Sweden. I help small and mid-sized organisations improve the booking, ordering and customer communication flows that their business depends on. Every engagement is led and delivered by me, with trusted specialists brought in for visual design or development when needed.

## How I work

Each project starts with a short discovery phase: interviews with staff and customers, a review of existing data and a walkthrough of the current tools. From there I sketch options, test them with real users and deliver working changes in small increments, so you see progress every two weeks. You get a shared project board, a written summary after every workshop and a fortnightly status note.

## Scope

Pre-arrival email journey in Swedish, English and German, a mobile check-in form, and upsell offers for breakfast, room upgrades and late checkout. Spa booking is left out because the spa system has no API.

## Fees and payment

The total fee is EUR 16,500, payable 30% on signing (EUR 4,950), 40% when the email journey is live in the first hotel (EUR 6,600) and 30% at handover (EUR 4,950).

## Timeline

Work runs from July to September 2025, after the peak of the high season, starting in Visby.

## Warranty

Defects reported within 45 days of launch are fixed at no extra cost.

## Assumptions

- You nominate one decision maker who can approve designs within five working days.

- You provide access to analytics, the current system and the relevant staff.

- Travel within Sweden is included. Travel outside Sweden is billed at cost.

- Prices are in euro and exclude VAT.

## Next steps

If this proposal looks right, reply to confirm and I will send a services agreement for signature. This proposal is valid for 30 days from the date above.

Maya Lindqvist

maya@lindqvist-consulting.se | +46 70 214 88 31